## project-management-lo
Project management Lofthus Frukt og Saft
Group Title
Name | Planning | Planning | Planning | Planning | Planing | Design and content | Design | Design | Design | Dedign | Developing | Developing | Developing | Developing | Developing | Testing | Testing | Testing | Testing | Done
Lofthus frukt og saft
Project start | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
Frontend-developer | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
and customer | Week 1 Day 1: Meeting with Custmer
Frontend-developer | Week 1 Day 1: Overview with CM
Designer | Week 1 Day 2: Meeting with employees
Frontend-developer
Designer | Week 1 Day 3: Research
Frontend-developer
Designer | Week 1 Day 4: Strategic planning
Frontend-developer
Copywriter | Week 1 Day 5: Meeting with Designer
Designer | Week 2 Day 6: Project start
Frontend-developer | Week 2 Day 6: Styletile
Copywriter | Week 2 Day 8: Site structure; Week 2 Day 9: Site structure
Designer | Week 2 Day 7: Text content
Photographer
Frontend-developer | Week 2 Day 8: Pictures; Week 2 Day 9: Pictures Editing
Frontend-developer | Week 2 Day 10: Last meeting with all; Week 3 Day 11: Wireframe
Frontend-developer | Week 3 Day 12: Coding and site build
Frontend-developer | Week 3 Day 13: Status meeting; Week 4 Day 16: Meeting with developer
customer | Week 4 Day 17: meeting with developers
Frontend-developer, | Week 3 Day 13: information meeting; Week 4 Day 16: customer; Week 4 Day 17: feedback from custmer
designer and copywriter | Week 3 Day 14: Testing new website; Week 4 Day 18: tes with all devices
Frontend-developer, | Week 3 Day 15: meeting between develpoer and designer; Week 4 Day 19: fixing some changing
Copywriter
customer, designer | Week 4 Day 19: done with docomentation; Week 4 Day 20: Meeting with custmer
Done